## Sheet1
Project Budget
| Source of Funds | Date Secured |  | GOCO Grant Request | Applicant Match ($) | Partner Match ($) | Total Funding ($)
CASH
| Town of Protivin | 2011-01-11 |  |  | 466598 |  | 466598
| Great Outdoors Colorado | 2012-06-19 |  | 300000 |  |  | 300000
| Generous Foundation | 2012-04-01 |  |  |  | 202920 | 202920
IN-KIND
| ABC Custom Playgrounds | 2012-08-01 |  |  |  | 2800 | 2800
| Lawn Wranglers | 2012-08-01 |  |  |  | 6062 | 6062
TOTAL SOURCE OF FUNDS |  |  |  | 300000 | 466598 | 211782 | 978380
CASH | Use of Funds | Number of Units | Cost Per Unit | GOCO Funds | Applicant Funds | Partner Funds | Total Funding ($)
Design
Excellent Design | Planning and Design |  |  |  | 10000 |  | 10000
Demolition
The Demo Crew | Clear and Grub - frontloader | 11.4 hours | 100 / hour |  | 1140 |  | 1140
Earthwork
True Excavating & Finishing Co. | Excavation and Embankment | 47 hours x 3 workers | 100 / hour |  | 14100 |  | 14100
Mile High Youth Corps | Removal of existing fence | 2 weeks | 5460 / week |  |  | 10920 | 10920
Installation of new fencing
Construction of Perimeter Trail
Utilities
Excel | Site Electrical | 417 feet of cable | $24 / foot |  | 10008 |  | 10008
Playground
ABC Custom Playgrounds | Playground Equipment | 1 | 100000 |  |  | 100000 | 100000
Site Lighting
Nattinger's Lighting Co | Parking Lot Lighting | 7 lights, poles electrical | 3571.43 | 15000 |  | 10000 | 25000
Nattinger's Lighting Co | Access Road Lighting | 4 lights, poles, electrical | 3750 |  | 15000 |  | 15000
Pedestrian Paving
We-Pave-It | Concrete Trail/Sidewalk | 280 yards | $150/ yard |  | 16000 | 26000 | 42000
Parking & Roadways
We-Pave-It | Curb & Gutter - Parking Lot | 162 yards | $150/ yard | 24300 |  |  | 24300
We-Pave-It | Asphalt Paving - Parking Lot | 500 yards | $100 / yard |  |  | 50000 | 50000
We-Pave-It | Curb & Gutter - Roadway | 20 yards | $150/ yard |  |  | 3000 | 3000
We-Pave-It | Asphalt Paving - Roadway | 30 yards | $100 / yard |  |  | 3000 | 3000
We-Pave-It | Curb Ramps | 20 yards | $150/ yard |  | 3000 |  | 3000
Fields
Smith and Smith | Fine Grading | 550,000 sq. ft. | 0.1 / sq. ft | 27500 | 27500 |  | 55000
Smith and Smith | 6" Topsoil (material and install) | 10,200 CY | 42 / cy | 214200 | 214200 |  | 428400
Smith and Smith | Seeding/hydromulch | 55,000 SY | 2.5/sy | 4750 | 132750 |  | 137500
Smith and Smith | Evergreen Trees 6' Hgt. | 13 trees | $150 / tree |  | 1950 |  | 1950
Smith and Smith | Evergreen Trees 8' Hgt. | 30 trees | $150 / tree |  | 4500 |  | 4500
Irrigation
The Irrigators | Sports Field Rotors | 200 rotors | $80 / rotor | 8000 | 8000 |  | 16000
The Irrigators | Controller | 1 Controller | 7500 | 3750 | 3750 |  | 7500
The Irrigators | Pipe | 5000 feet | $0.5 / foot | 2500 |  |  | 2500
Site Furnishings
Fellows, Inc. | Benches | 12 Benches | $200 / bench |  | 2400 |  | 2400
Fellows, Inc. | Bike Racks | 2 Bike Racks | $650 / rack |  | 1300 |  | 1300
Fellows, Inc. | Trash Containers | 10 Trash containers | 100 / trash can |  | 1000 |  | 1000
USE OF FUNDS - CASH SUBTOTAL |  |  |  | 300000 | 466598 | 202920 | 969518
IN-KIND | Use of Funds | No. of Units / Hours / Acres | Cost Per Unit / Hour / Acre | GOCO Funds | Applicant Funds | Partner Funds | Total Funding ($)
Professional Services | [6 empty] | 0
ABC Custom Playgrounds | Installation of Playground Equip | 20 hours / 4 workers | 20 |  |  | 1600 | 1600
ABC Custom Playgrounds | Site Preparation | 15 hours / 4 workers | 20 |  |  | 1200 | 1200
Materials | [6 empty] | 0
Lawn Wranglers | Sod | 9524 sq. ft. | $0.50 per sq. ft. |  |  | 4762 | 4762
0
Equipment | [6 empty] | 0
Lawn Wranglers | Dump Truck & Operator | 10 hours | 130 |  |  | 1300 | 1300
| USE OF FUNDS - IN-KIND SUBTOTAL |  |  | 0 | 0 | 8862 | 8862
| 10% Contingency |  |  | 0 | 0 | 0 | 0
| TOTAL PROJECT COST |  |  | 300000 | 466598 | 211782 | 978380
Remember: the Total Project Cost row must equal the Total Source of Funds row above
CALCULATION OF MATCH REQUIREMENTS
Item | Explanation | Requirement | Actual | Meets Requirement?
Minimum Match | 25%/Total Costs | 244595 | 678380 | Yes
Minimum Cash Match | 10%/Total Costs | 97838 | 669518 | Yes
CALCULATION OF GOCO %
GOCO % of Total Costs | 30.66%